## Atlas Core Plan
ID | Workstream | Task | Owner | Start | End | Depends On | Status | % Complete | Notes
C-01 | Governance | Finalize program charter & RACI | Priya Nair | 2026-09-28 | 2026-10-02 |  | Complete | 100
C-02 | Infrastructure | Target architecture sign-off | Sara Ostrowski | 2026-10-05 | 2026-10-16 | C-01 | Not Started | 0
C-03 | Infrastructure | Provision production cluster | Sara Ostrowski | 2026-10-12 | 2026-10-30 | C-02 | Not Started | 0 | Hardware lead time is the main risk
C-04 | Infrastructure | Network & firewall configuration | Sara Ostrowski | 2026-11-02 | 2026-11-06 | C-03 | Not Started | 0
C-05 | Payments | Migrate core payment service to new cluster | Marcus Chen | 2026-11-02 | 2026-11-13 | C-03 | Not Started | 0 | Refund endpoint intermittent timeouts (~1 in 200 under load) still being profiled
C-06 | Payments | Design API rate limiting | Marcus Chen | 2026-10-12 | 2026-10-23 | C-02 | Not Started | 0 | Final limits needed by partner integrations
C-07 | Data | Data migration dry run #1 | Tom Reyes | 2026-11-16 | 2026-11-20 | C-05, V-05 | Not Started | 0 | Needs CloudBridge migration scripts
C-08 | QA | Regression testing - core flows | Lena Alvarez | 2026-11-16 | 2026-11-20 | C-05 | Not Started | 0 | Marcus supporting
C-09 | QA | Load & performance testing | Lena Alvarez | 2026-11-23 | 2026-11-27 | C-08, C-07 | Not Started | 0 | Assumes PayNet integration complete by Nov 20. Blocked until refund timeout fixed.
C-10 | QA | User acceptance testing (UAT) | David Kim | 2026-11-30 | 2026-12-03 | C-09 | Not Started | 0
C-11 | Governance | Go/No-Go decision | Priya Nair | 2026-12-04 | 2026-12-04 | C-10 | Not Started | 0
C-12 | Cutover | Production cutover | Marcus Chen | 2026-12-07 | 2026-12-07 | C-11 | Not Started | 0 | Target cutover date: Dec 7
C-13 | Cutover | Hypercare | Sara Ostrowski | 2026-12-07 | 2026-12-18 | C-12 | Not Started | 0