## CloudBridge Plan
Milestone ID | Deliverable | Responsible | Planned Start | Planned Finish | Prerequisites | RAG | Comments
V-01 | Kickoff & access provisioning | Dana Whitfield | 2026-10-05 | 2026-10-09 | Core program charter | Green
V-02 | Source system discovery | Raj Patel | 2026-10-12 | 2026-10-23 | V-01 | Green
V-03 | Install monitoring agents on production cluster | Raj Patel | 2026-10-26 | 2026-11-06 | Core: production cluster provisioned | Green | Assumes cluster is available by 23-Oct
V-04 | Configure monitoring dashboards & alerting | Mei Lin | 2026-11-09 | 2026-11-20 | V-03 | Green
V-05 | Deliver data migration scripts | Raj Patel | 2026-10-26 | 2026-11-20 | V-02 | Amber | Open schema questions outstanding from client data team
V-06 | Dry-run support | Raj Patel | 2026-11-16 | 2026-11-20 | V-05 | Green
V-07 | Production cutover support | Dana Whitfield | 2026-12-11 | 2026-12-14 | Client Go/No-Go | Green | Cutover planned 14-Dec per SOW
V-08 | Hypercare | Dana Whitfield | 2026-12-14 | 2026-12-23 | V-07 | Green | Vendor change freeze begins 18-Dec through 04-Jan; reduced holiday coverage
V-09 | Final handover & knowledge transfer | Mei Lin | 2027-01-04 | 2027-01-08 | V-08 | Green