## PayNet Integration
Task # | Task Name | Lead | Start Date | Duration (working days) | Blocked By | % Done | Risk Notes
PA-1 | Requirements review with Atlas payments team | Elena Rossi | 2026-10-05 | 5 |  | 0
PA-2 | Gateway API contract update | Elena Rossi | 2026-10-12 | 10 | PA-1 | 0 | Needs final rate-limit values from Atlas core team
PA-3 | Build integration against new Atlas API | Sam Okafor | 2026-10-26 | 15 | PA-2 | 0
PA-4 | Integration testing in Atlas staging | Sam Okafor | 2026-11-16 | 10 | PA-3 | 0 | Needs Atlas SME (Marcus Chen) ~50% for the 2 weeks
PA-5 | Card processor certification | Elena Rossi | 2026-11-30 | 10 | PA-4 | 0 | Slots only on Mondays; ~2 week turnaround
PA-6 | Refund flow validation | Sam Okafor | 2026-11-16 | 5 | Atlas refund endpoint timeout fix | 0 | Marcus Chen walkthrough needed
PA-7 | Go-live readiness review | Elena Rossi | 2026-12-07 | 3 | PA-5 | 0
PA-8 | Production cutover support | Sam Okafor | 2026-12-14 | 5 | PA-7 | 0 | Cutover week of Dec 14