## Data & Security Plan
Workstream | Activity | Owner | Start | Finish | Dependencies | Status | Notes
Security | Security architecture review | Nadia Hassan | Oct 19 | Oct 30 | Atlas architecture sign-off | On Track
Privacy | Data retention & privacy impact assessment | Nadia Hassan | Oct 26 | Nov 13 |  | On Track
Analytics | Build analytics ingestion pipeline | Omar Bell | Nov 2 | Nov 25 | Vendor log forwarding / agent output | At Risk | Waiting on vendor to confirm log format
Security | Staging environment freeze | Nadia Hassan | Nov 16 | Nov 16 | Atlas staging stable | On Track | Milestone
Security | Penetration test & PCI control assessment | Nadia Hassan | Nov 16 | Dec 4 | Staging freeze | On Track | Needs 1 Atlas engineer (Marcus Chen) ~50% for walkthroughs, Nov 16-27
Security | Remediation of findings | Nadia Hassan | Dec 7 | Dec 11 | Pen test results | On Track | Critical findings block go-live
Compliance | Compliance sign-off | Nadia Hassan | Dec 11 | Dec 11 | Remediation | On Track | Milestone. Cutover Dec 7 per Atlas plan
Analytics | Analytics dashboards go-live | Omar Bell | Dec 14 | Dec 18 | Ingestion pipeline; Atlas cutover | On Track